Assignment 6

1) How do you evaluate the performance of a project in agile?

The key measures for evaluating agile project performance are:

Velocity

V=Units of efforts completed/ Sprint

Velociy for first release plan is predicted which is created during project initiation after that actual velocity is measured at each timebox and this actual measure is used to predict the velocity for subsequent timeboxes in the release plan.

Hit rate
Percentage of work allocated to a timebox that was actually completed.

Work remaining on tasks
Each day the remaining work is estimated on each task.

Project cost
It is estimated to make sure that the project is completed within the budget.

Three management measures are:

i) Cost performance index (CPI)

Cost Performance Index (CPI) = (Baseline Cost per Story Point)/(Actual Cost per Story Point)
CPI > 1 is an indication that cost incured for the project is less than what expected .
CPI<1 is an indication that the cost has exceeded the expected value.
CPI	=	EV/TAC
=	(BC/SP)/(AC/SP)
ii) Schedule performance index (SPI)

Schedule Performance Index (SPI) = (Actual Velocity/Baseline Velocity)

SPI > 1 is an indication that the project has finished earlier than expected.
SPI < 1 is an indication that the project has finished late than expedcted.
SPI	=	EV/PV
=	AV/BV

iii) Earned business value (EBV)

Earned value is defined as “the value of work completed”
EV=total story points times the baseline cost per story point

If project goes according to the plan CPI and SPI would be = 1 for every Sprint

Based on the SPI and CPI values we can understand whether the project is going on time and on budget. Thus it helps determine the performance of a project.

The CPI and SPI does not check for the business value. The business value measures the outcome and not the outputs. It checks whether the customer satisfaction is guaranteed.

2) Compare traditional monitoring & control with agile monitoring & control with respect to metrics generation?

Traditional monitoring & control	Agile monitoring & control
It is very concerned about observing and measuring actual project performance against the plan and fixing it if it varies.	It also measures project performance against the planned value, but also takes account of business value.
Variance from the plan is considered bad unless it is approved by Change Management.	Variation is not considered bad and changes plan to suit the current position.
Traditional project monitoring focuses on tracking how much effort is expended on each task.	The main Agile monitoring technique is to track what software has been incrementally delivered.
Delivery of the working software is done only after the development.	Frequent delivery allows the Product Owner to declare a product “done” at any time or the Business Sponsor to declare the project finished at any time
Communication can be of any form and does not restrict in any way.	Agile teams try to promote face-to-face communication and to reduce the channels of communication.
Not focused on colocation.	Colocation is done to ensure successful communication between the agile teams.
No burn down charts are created here.	Results are demonstrated using the burn down chart.
Comparing plans is the measure of progress.	Emphasizing customer value and working software are the primary measure of progress.
Delivery of software is only done after the final developement, hence customer is invloved only at the user acceptance testing.	Highest priority is to satisfy the customer through early and continuous delivery of valuable software.
Product demo is done at the UAT.	The Product Demonstration at the end of a Timebox

3) With a total project budget of $ 175,000, and having completed one out of four Iterations, we have this product backlog and these actuals:

Feature	Estimate / (storypoints)	Completed / (storypoints)	Actual Cost (1000s / dollars)
Welcome Screen	10	10	15
Advert - Splash Screen	20	20	30
Login Screen	10	10	20
Personalized Google Ads	20
Catalog Browser	20
Catalog Editor	10
Shopping Basket Browser	5
Shopping Card Editor	25
Check-out Process	20
Invoice Calculation	10
Credit Card Verification	10
PayPal Payment Handling	20
Order Confirmation Email	20
Totals	200	40	65

in our example, after Iteration 1 we should be at 25% complete)
- Calculate Planned Value
- Actual % Complete
- Earned Value
Ans)

Total project budget = $175000
Planned Value = Expected Percent Complete * Total Budget
=25% * $175,000
= $43,750

Actual Percent = total number of storypoints completed / total number of storypoints estimated

= 40 / 200
= 20%

Earned Value	= Actual Percent Complete * the Total Budget
= 20% *$175,000
= $35,000